## Schedule
Date | Task | Description | Priority | Time per task | Progress | Comments
2021-02-02 | WBS | Do This Page | 0 | 2 | Done | Hopefully this is acceptable to the committee
2021-02-05 | Feature Specs | Do the Feature Spec. | 0 | 2 | Done | Hopefully this is acceptable to the committee
2021-02-09 | GitHub, Unity, etc. | Set up GitHub, Unity, gitignore, etc. | 0 | 1 | Done
2021-02-12 | Research different assets | Do some research for what I'm looking for | 0 | 1 | Done
2021-02-23 | Add player Asset | Grab an asset for a car from the asset store and build an easy terrain so I can start with testers | 0 | 1 | Done
2021-02-26 | Add defualt terrain | Add a simple terrain so testers can have something to work with to get a feel for how the player works | 0 | 0.5 | Done | Ready for Testers
2021-03-02 | Start with testers | Get Testers set up and emphasise on how they are focusing currently on pefecting how the car feels in the enviornment | 0 | 1
2021-03-05 | Main Menu | Add a simple main menu screen and make sure it works in a WebGL build | 0 | 1 | Done | Done for Now
2021-03-09 | Pause Screen | Add a simple pause screen and make sure it works in a WebGL build | 0 | 1 | Done
2021-03-12 | Finalize everything prior | Publish new version of game including Pause and main menu screens | 0
2021-03-16 | Build a track | Create a new Scene and build a terrain for it and get a track asset | 0 | 1.5 | Done
2021-03-23 | Build a track | Create the track and add decorations to the scene | 0 | 1.5 | Done
2021-03-26 | Finalize Track | Finalize anything else for freeplay mode and publish | 0
2021-03-30 | Beat the clock mode | Add the beat the clock mode into the game | 1 | 1
2021-04-02 | Game selection day | Find a way to get the game to know which mode to do | 1 | 1.5
2021-04-06 | Finalize Beat the clock mode | Finalize beat the clock mode and publish | 1
2021-04-09 | CPU ghost racer | Research how a cpu ghost racer could work | 2 | 1
Spring Break | CPU ghost racer | Add Waypoints | 2 | 1
2021-04-20 | CPU ghost racer | Get CPU to follow Waypoints | 2 | 2
2021-04-23 | CPU ghost racer | Get CPU to follow Waypoints | 2 | 2
2021-04-27 | Finalize CPU ghost racer | Finalize ghost racer and publish | 2
2021-04-30 | CPU race against player | Research how CPU could race against player | 3 | 2
2021-05-04 | CPU race against player | Research how CPU could race against player | 3 | 2
2021-05-07 | CPU race against player | Implement CPU racing against player | 3 | 6
2021-05-11 | CPU race against player | Implement CPU racing against player | 3 | 6
2021-05-14 | CPU race against player | Implement CPU racing against player | 3 | 6
2021-05-18 | CPU race against player | Implement CPU racing against player | 3 | 6
2021-05-21 | CPU race against player | Implement CPU racing against player | 3 | 6
2021-05-25 | CPU race against player | Implement CPU racing against player | 3 | 6
2021-05-28 | Finalize AI CPU race | Finalize CPU racing against player | 3 | 6
2021-06-01 | Bug Fixing |  | 0 | ?
2021-06-04 | Bug Fixing |  | 0 | ?
2021-06-08 | Bug Fixing |  | 0 | ?
2021-06-11 | Bug Fixing |  | 0 | ?
2021-06-15 | Presentation to AP CS |  | 0 | ? |  | I DID IT!!!
2021-06-17 | Graduation | Graduation | Graduation